## Team1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team 1 | 23-12-2024 | Promotional Notifications not being correctly sent to specified user mail | Sprint 2 | Team 1 | Logical | Rectified the backend notification flask url functions and integrated properly with front end ensuring seamless connection | 28-12-2024 | Closed | Completed
2 | Team 1 | 17-01-2025 | Revenue Generation Graphs not visualized properly( Axes Titles Nomenclature and integration issues in main admin page) | Sprint 3 | Team 1 | User Interface | Corrected the backend graph (Matplotlib) logic | 19-01-2025 | Closed
3 | Team 1 | 25-01-2025 | Integration of Frontend and Backend ( Team 1 Integration) | Sprint 3 | Team 1 | Maintainability | Currently working on rectifiying | Ongoing | Open | Ongoing

## Team2
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | User Interface | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team 2 | 21-12-24 | Status change on dashboard not reflecting on the orders page. Should update on both and sync. | Sprint 2 | Team 2 | Logical | Investigated and found missing integration between dashboard and orders page after status change. | 25-12-24 | Closed
2 | Team 2 | 25-01-25 | 500 INTERNAL SERVER ERROR in the test_checkout_post_invalid_delivery_location due to database access issue. | Sprint 3 | Team 2 | Maintainability | Investigated and found database connection error due to incorrect user credentials. | 28-01-25 | closed
3 | Team 2 | 25-01-25 | INTERNAL SERVER ERROR in the test_checkout_post_successful_order due to database access issue. | Sprint 3 | Team 2 | Maintainability | Investigated and identified database connection error. | 29-01-25 | Open

## Team3
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team 3 | 23-12-2024 | Integration of Frontend and Backend | Sprint 1 | Team 3 | Maintainability | Currently working on rectifiying | 23-12-2024 | Closed | Completed
2 | Team 3 | 2025-06-01 | In Orders Overview page for Weekly Status dates are showing in an incorrect way | Sprint 2 | Team 3 | Logical |  | 2025-06-01 | Closed | Completed
3 | Team 3 | 22-01-2025 | In Order Management if the status is in completed and if we update that button and if we select cancel the order is showing cancelled | Sprint 3 | Team 3 | Logical |  | 22-01-2025 | Closed | Completed

## Team4
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks

## Team5
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks

## Sheet2
Logical
User Interface
Maintainability
Standards
Others