## Team 1
SPRINT 1
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 6692960 | 21-12-2024 | SCS Balaji | Integrating static url links in front end in correspondence to routes in Flask | While integrating with backend, faced issues in static css and media links, so not to include conventional CSS and images links while integrating with Flask-routes | Ensuring proper Flask route integration for static files | Ensured proper static linking guidelines in Flask
2 | Sprint 1 | 6692960 | 21-12-2024 | Gokul N | Interconnect relations and mention the mismatching names in frontend and backend | Right and Left joined wrongly in database tables | Analyzing database relationships carefully | Corrected database joins and verified relationships.
3 | Sprint 1 | 6692960 | 21-12-2024 | Panchadip | Regularly updating the GitHub Repository by all the team members and resolving conflicts thereafter | Delays in commiting project tasks to repo | Continue to attend regular meets and collaborate with other members regarding the daily task updates | Encouraging the active participation of all team members
4 | Sprint 1 | 6692960 | 21-12-2024 | Madhu Keerthi | Resolving the CSS conflicts | CSS images and links must be interconnected with Flask routes | Using static url links for flask with CSS pages | Discussed the Flask routing applications with concerned team members
5 | Sprint 1 | 6692960 | 21-12-2024 | All members | Setting clear goals and priorities for the sprint in the initial stages | Working on tasks without proper planning or prioritizing | Supporting each other to resolve the challenges and team collaboration | Setting clear deadlines and proper planning for successful completion of the sprint
SPRINT 2
6 | Sprint 2 | 27-12-2024 | 2025-07-01 | All members | Try to enhance active participation and contributions in group discussions. | Refrain from remaining silent during discussions; actively contribute and share your perspectives | Supporting each other effectively in resolving challenges and fostering team collaboration. | Team members actively participated in group discussions, providing constructive feedback and ensuring all viewpoints were considered.
7 | Sprint 2 | 27-12-2024 | 2025-07-01 | All members | Focus on understanding the requirements thoroughly before implementation. | Maintaining efficient communication among all members | Collaborating effectively to identify and clarify ambiguities in task requirements before implementation. | Regular brainstorming sessions through were held to discuss and address unclear task requirements, ensuring a seamless workflow.
8 | Sprint 2 | 27-12-2024 | 2025-07-01 | Panchadip | Work on time management and setting clear priorities for tasks. | Maintaing time efficiently and contributing to the tasks and stop any delays in task submissions | Managing tasks with a structured approach while ensuring all team deadlines are consistently met. | Created and adhered to a shared schedule( to discuss updates through Whatsapp groups) to enhance task prioritization and timely completion.
9 | Sprint 2 | 27-12-2024 | 2025-07-01 | Madhu Keerthi | Try to collaborate more effectively and provide regular updates during stand-ups. | Not attending the stand-up meets / not participating in discussions | Providing consistent updates during stand-ups and contributing actively to discussions for improved team coordination. | Stand-ups were conducted daily, with all members sharing progress and challenges, fostering a more aligned and collaborative environment.
10 | Sprint 2 | 27-12-2024 | 2025-07-01 | SCS Balaji/ Gokul N | College timings and exam related conditons resulting in delay of tasks | Make a schedule for the tasks and avoid working without planning the task | Supporting each other to resolve the challenges and team collaboration and Allocating time judiciously to balance college commitments and project deadlines effectively. | Adjusted sprint timelines to accommodate academic schedules, ensuring team members could meet deliverables without compromising academic performance.
11 | Sprint 2 | 27-12-2024 | 2025-07-01 | Gokul N | Clarification of task requirements (if any confusion) before the implementation of the task | Working on tasks without proper planning or prioritizing | Addressing task dependencies and ensuring all requirements are clarified early for smooth implementation. | Conducted requirement analysis meetings to clarify task goals, enabling better planning and execution throughout the sprint.
12 | Sprint 2 | 27-12-2024 | 2025-07-01 | Panchadip/SCS Balaji | Monitoring each task from starting till execution in Github | Carefully handling Github operations and always communicating with team members in case of any doubts related to github operations | Continuously tracking progress in GitHub to ensure smooth task management and avoid conflicts during implementation. | Introduced a GitHub workflow guide to streamline task tracking and reduce merge conflicts, ensuring efficient use of version control.
SPRINT 3
13 | Sprint 3 | 2025-10-01 | 23-01-2025 | Panchadip/SCS Balaji | Openly share your ideas and try to communicate with team more often | Not putting forward your ideas, suggestions or any changes to be implemented | Openly communicating whatever suggestions one has to put and implement any changesn to be made | Created an open collaborative environment for discussing and implementing changes; introduced specific doubt groups for enhancing communications and clarity among all
14 | Sprint 3 | 2025-10-01 | 23-01-2025 | Madhu Keerthi | Checking each task from starting till execution in Github by regular updation | Carefully handling Github operations and always communicating with team members in case of any doubts related to github operations | Continuously tracking progress in GitHub to ensure smooth task management and avoid conflicts during implementation. | Introduced a GitHub workflow guide to streamline task tracking and reduce merge conflicts, ensuring efficient use of version control.
15 | Sprint 3 | 2025-10-01 | 23-01-2025 | Tejasri G | Monitoring push/pull changes while checking execution in Github | Carefully handling Github operations and always communicating with team members in case of any doubts related to github operations | Carefully mitigate any potential issues that may arise | Introduced a GitHub workflow guide to streamline task tracking and reduce merge conflicts, ensuring efficient use of version control.
16 | Sprint 3 | 2025-10-01 | 23-01-2025 | All Members | Slove the issues which comes up more efficiently | Carefully tackle the existing issues and try to find a way for solving the problems | Help each other in task completion whenever required | Introduced specific community groups for open communication among all and discussions
17 | Sprint 3 | 2025-10-01 | 23-01-2025 | Gokul/SCS Balaji | Providing regular work updates | Not communicating work updates/ Not joining daily scrum meets | Continue analyzing problems effectively and resolving blockers promptly | Regularly conducting scrum meets typically ranging from 1-1.5 hrs
18 | Sprint 3 | 2025-10-01 | 23-01-2025 | Panchadip/Gokul | Manage to complete assinged task | Delaying existing assigned tasks without proper intimation | Collaborate with all team members | Introduced and encouraged everyone to communicate and interact regarding team works more effectively

## Team 2
SL# | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 14/12/2024 | 20/12/2024 | Indrajeet | Try to make the team more collaborative by ensuring effective communication between the frontend, backend, and database teams. | Some of the coding tasks were delayed, causing a setback in meeting the deliverables on time. | Being punctual and responsible, helping everyone, maintaining and organizing tasks, ensuring timely meetings | Praised for his leadership and organizational skills
2 | Sprint 1 | 14/12/2024 | 20/12/2024 | Likhita | Collaborate with the team, use existing projects for development | Writing static code | showing efforts in contribution | Encouraged pair programming and regular code reviews
3 | Sprint 1 | 14/12/2024 | 20/12/2024 | Bhargavi | Make the database more consistent and ensure regular communication with the backend team for smooth integration and updates. | Ensure that you make only essential updates to the code, avoiding any unnecessary modifications. | Assisting Varshita, being regular in meetings | Acknowledged her support to Varshita in team meetings
4 | Sprint 1 | 14/12/2024 | 20/12/2024 | Varshitha | Try to create a prototype of the UI before starting the coding process to visualize the design and functionality. | Ensure that you make only essential updates to the code, avoiding any unnecessary modifications. | Attending all meetings, completing tasks on time | Front end contributions are highly valued and appreciated
5 | Sprint 1 | 14/12/2024 | 20/12/2024 | Kunal | Add an inline editing feature for faster updates | Try to update the code on time to ensure smooth progress and meet deadlines. | Seamless integration into UI and backend, updating existing menu items | Implemented validation checks for edited data
6 | Sprint 1 | 14/12/2024 | 20/12/2024 | Harsh | Make the code cleaner to improve readability for future reference and easier maintenance. | Attend stand-ups on time to ensure everything is going smoothly. | Being obedient, attending all meetings, helping others | Recognized his contributions in team meetings
7 | Sprint 1 | 14/12/2024 | 20/12/2024 | Randeep | Make the code cleaner to improve readability for future reference and easier maintenance. | Ensure timely code updates to maintain smooth progress | Attending all meetings, completing tasks, managing GitHub repo, writing backend code | Appreciated his consistent efforts in maintaining the repository and Back end contributions
Sprint 2
1 | Sprint 2 | 26/1/2025 | 2025-07-01 | Indrajeet | Try to maintain a base code more efficiently | - | Encouraging creativity among team members to incorporate additional functionalities | Praised for his leadership and organizational skills
2 | Sprint 2 | 26/1/2025 | 2025-07-01 | Likhita | Try To Be more active in Groups and interact more with your team mates | Stop being much inactive | Continue doing the front end efficiently | Ensured Contributing in front end
3 | Sprint 2 | 26/1/2025 | 2025-07-01 | Bhargavi | Try To Be more active in Groups and interact more with your team mates | Stop being much inactive | Contunie doing the front end efficiently | Ensured Contributing in front end
4 | Sprint 2 | 26/1/2025 | 2025-07-01 | Varshitha | Try To Add comments in the code which you have modified | Ensure Front end Glitches,before subimitting tasks | Continue doing the front end efficiently,Attending all meetings, Completing all taks on time | Ensured Less conflicts while implementing frontend
5 | Sprint 2 | 26/1/2025 | 2025-07-01 | Kunal | Try To be more active and collaborative to team | Stop being much absent and uncollaborative | Continue doing backend tasks efficiently, completing all tasks on time | Imlemented Regularity in Joining Standup meets
6 | Sprint 2 | 26/1/2025 | 2025-07-01 | Harsh | - | Ensure attending standups on regular basis | Continue setting up/manage data bases efficiently,completing all taks on time | Ensured Joining the standup meets
7 | Sprint 2 | 26/1/2025 | 2025-07-01 | Randeep | Try to add comments and make sure of the code you are implementing is working fine | Ensure Code Consistency Before submitting tasks | continue doing problem solving of backend efficiently,,atttending all meetings | Collaboratively worked with team and contributed in many things including pushing the code into github
Sprint 3
1 | Sprint 2 | 2025-10-01 | 23/1/2025 | Indrajeet | Avoid being inactive during stand-ups. | Try to be more active and engaged in stand-up meetings. | Continue providing updates and contributing to discussions during the meets. | Became more consistent in attending stand-ups and actively participating.
2 | Sprint 2 | 2025-10-01 | 23/1/2025 | Likhita | Try to communicate with the team mates in the meets | Try to communicate openly with teammates during discussions. | Continue sharing progress and challenges clearly in meetings. | Improved team interactions by actively sharing ideas and feedback in discussions.
3 | Sprint 2 | 2025-10-01 | 23/1/2025 | Bhargavi | Don’t hesitate to share your ideas and try to communicate with team more often | Actively put forward your ideas and suggestions for team tasks | Continue contributing innovative and practical solutions for ongoing projects. | Encouraged brainstorming sessions to create a safe space for sharing ideas.
4 | Sprint 2 | 2025-10-01 | 23/1/2025 | Varshitha | Try to manage between everything within the time | Always try to divide the work among the team. | Continue balancing tasks while meeting deadlines. | Implemented a task prioritization system to divide work efficiently among members.
5 | Sprint 2 | 2025-10-01 | 23/1/2025 | Kunal | Try to slove the issues arised more efficiently | Always try to find a way for solving the problems | Continue analyzing problems effectively and resolving blockers promptly | Conducted collaborative problem-solving sessions to handle critical issues.
6 | Sprint 2 | 2025-10-01 | 23/1/2025 | Harsh | Try to respond to messages more often within the time | - | Continue being accessible and approachable for clarifications or assistance. | Improved communication turnaround time by actively checking and responding to messages.
7 | Sprint 2 | 2025-10-01 | 23/1/2025 | Randeep | Try to join the team meets more regularly | Dont miss the standup meets | Continue contributing updates and feedback during all team meetings. | Ensured preparing updates beforehand.

## Team 3
SL# | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
Sprint - 1
1 | Sprint 1 | 6692960 | 21-12-2024 | Dhruthi | Facilitate effective communication among the frontend, backend, and database teams to enhance team collaboration | Delays in completion of assigned tasks | Regularly updating the task completion | Ensuring overall collaboration in the entire team
2 | Sprint 1 | 6692960 | 21-12-2024 | Sanjay | Regular updation of the GitHub Repository by all the team members | Delays in initiating project tasks | Continue conducting the standup meetings | Ensuring the overall participation of all the members and early assignment of tasks
3 | Sprint 1 | 6692960 | 21-12-2024 | Mahalakshmi | Setting clear goals and priorities for the sprint in the initial stages | Working on tasks without proper planning or prioritizing | Supporting each other to resolve the challenges and team collaboration | Setting clear deadlines and proper planning for successful completion of the sprint
4 | Sprint 1 | 6692960 | 21-12-2024 | Sameer | Overall contribution to all the domains by all members and ensuring proper communication | Delays in dependent tasks (Designing , Frontend) | Completion of assigned tasks by all the team members | Ensuring the participation of all members in all the tasks
5 | Sprint 1 | 6692960 | 21-12-2024 | Seran | Completion of tasks assigned to each team member regularly | Delay tasks assignment | Coordinating among all the members | Ensuring daily progress of tasks assigned
6 | Sprint 1 | 6692960 | 21-12-2024 | Mahesh | Begin regular peer reviews to ensure code quality and consistency. Focus on completing one feature thoroughly before starting another. | Avoid multitasking with too many features at once | Enhancing features and functionalities in the designing(UI) part | Ensuring step by step completion of assigned tasks
Sprint - 2
7 | Sprint 2 | 27-01-2025 | 2025-07-01 | Dhruthi | Encouraging creativity among team members to incorporate additional functionalities | - | Ensuring contribution from all the team members | Incorporating additional functionalities to enhance project outcome
8 | Sprint 2 | 27-01-2025 | 2025-07-01 | Sanjay | Clarification of task requirements (if any confusion) before the implementation of the task | Not mentioning the issues faced during the task completion (causing unexpected delays) | Regular interaction between team members | Ensuring clarity in the assigned tasks among the team members and informing doubts or queries (if any) at the earliest
9 | Sprint 2 | 27-01-2025 | 2025-07-01 | Mahalakshmi | Proper planning of tasks to avoid last-minute rush | - | Maintain efficient teamwork and open communication | Ensuring proper planning of tasks
10 | Sprint 2 | 27-01-2025 | 2025-07-01 | Sameer | Completion of tasks within the timeline and trying for more contribution apart from the assigned tasks | Not attending the stand-up meets | Regular interactions with the scrum master | Ensuring all team members attend the stand-up meets regularly and contribute more according to their availability
11 | Sprint 2 | 27-01-2025 | 2025-07-01 | Seran | Quicker response to resolve the issues arised | Delays in updates regarding task progress | Being organized and keeping the progress on track | Ensuring timely response to rectify the issues and daily updation of progress of all tasks to the team members
12 | Sprint 2 | 27-01-2025 | 2025-07-01 | Lally | - | - | Coordination among team members | Continuing to coordinate among the team members
13 | Sprint 2 | 27-01-2025 | 2025-07-01 | Mahesh | Collaborating with the team during the testing phase to catch edge cases and improve test coverage | - | Thorough and detailed testing to ensure the quality of deliverables and maintaining clear communication | Ensuring coordination among the team members during the testing phase
Sprint - 3
14 | Sprint 3 | 2025-10-01 | 23-01-2025 | Dhruthi | Analyze potential pitfalls or challenges for each task before initiating it. | - | Maintain effective team collaboration and regularly update tasks.
15 | Sprint 3 | 2025-10-01 | 23-01-2025 | Sanjay | - | Maintain effective team collaboration and regularly update tasks. | Continue showing initiative to complete tasks if someone else is unable to finish them.
16 | Sprint 3 | 2025-10-01 | 23-01-2025 | Mahalakshmi | - | - | Maintaining strong communication and collaboration within the team.
17 | Sprint 3 | 2025-10-01 | 23-01-2025 | Sameer | Track each task consistently from start to finish. |  | Coordinating with all team members
18 | Sprint 3 | 2025-10-01 | 23-01-2025 | Seran | Track each task consistently from start to finish. | - | Collaborate effectively and support each other's tasks.
19 | Sprint 3 | 2025-10-01 | 23-01-2025 | Lally | - | - | Maintain clear communication among team members.
20 | Sprint 3 | 2025-10-01 | 23-01-2025 | Mahesh | Trying to complete assinged task | - | Collaborate with all team members

## Team 4
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7

## Team 5
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7