## Team 1
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 - 10.12.2024 | Queries on User Stories | Discussed about implementing various User Stories for Product Backlog
Sprint 1 | Day 2- 11.12.2024 | Initial Flask Setup Doubts | Discussed about Product Backlogs
Sprint 1 | Day 3- 12.12.2024 | No Impediments | Discussed and listed all potential User Stories and distributed tasks among all interns
Sprint 1 | Day 4- 13.12.2024 | No Impediments | Finalized Tasks associated with User Stories, discussed about design implementation tasks and getting started with Front-End Tasks
Sprint 1 | Day 5- 16.12.2024 | No Impediments | Discussed on the overall Figma UI Prototyping for the sprint and updates on the front end tasks
Sprint 1 | Day 6- 17.12.2024 | Queries on Backend functionality processing | Discussed about the actions to be taken for resolving Backend conflicts (including the processing of conflicts within modules, establishing a proper virtual environment and creating a github repository for proper collaboration and sync between front end and backend team)
Sprint 1 | Day 7- 18.12.2024 | Queries on Testing and Database Tables | Finalized and reduced all the tables(to keep only the most important and relevant tables), updated members to proceed with appropriate testing methods
Sprint 1 | Day 8- 19.12.2024 | No Impediments | Discussed about our team presentation
Sprint 1 | Day 9- 20.12.2024 | No Impediments | Discussed about our team presentation
Sprint 2 | Day 10- 26.12.2024 | Queries on new User Stories for Milestone 2 | Discussed about setting up fundamental,must have as well as unique User Stories
Sprint 2 | Day 11- 27.12.2024 | No Impediments | Discussed about User Stories
Sprint 2 | Day 12- 28.12.2024 | Initial User Case Diagram doubts | Discussed about User Case Diagrams and User Stories Finalizations
Sprint 2 | Day 13- 29.12.2024 | No Impediments | Discussed about overall team project, Github Repository rules and guidelines for Milestone 2 and contribution process
Sprint 2 | Day 14- 30.12.2024 | No Impediments | Discussed about event flow for accessing various web pages within scope of our project topic
Sprint 2 | Day 15- 2.01.2025 | Initial doubts on must have user stories | Discussed about must have user stories and features to be implemented thereby, in a time bound setup
Sprint 2 | Day 16- 3.01.2025 | No Impediments | Discussed about overall updates
Sprint 2 | Day 17- 4.01.2025 | Queries on Flask routing and backend access | Discussed about overall flask routing applications with Front End
Sprint 2 | Day 18- 5.01.2025 | Queries on Event Flow for accessing various components of webpage | Discussed about event flow and working structure of various components
Sprint 2 | Day 19- 6.01.2025 | No Impediments | Discussed about our planning for team presentation
Sprint 3 | Day 20- 8.01.2025 | Queries on Backend functionality of Matplotlib graph processing | Discussed potential solution of integrating matplotlibs and explored StackOverflow and other useful websites for solution
Sprint 3 | Day 21- 10.01.2025 | No Impediments | Discussed overall updates
Sprint 3 | Day 22- 11.01.2025 | Queries on url integration on admin dashboard | Solved potential issues related to complete url integration with Flask
Sprint 3 | Day 23- 14.01.2025 | Queries on UI Format for admin dashboard | Discussed UI format with the team
Sprint 3 | Day 24- 15.01.2025 | Queries on Dashboard button changes | Solved potential issues related to button utility changes
Sprint 3 | Day 25- 16.01.2025 | Queries on finalizing the user schematics, visualization placement in the dashboard | Discussed the potential changes and updates
Sprint 3 | Day 26- 17.01.2025 | No Impediments | Discussed overall updates
Sprint 3 | Day 27- 18.01.2025 | Queries on SQL installation and set up | SQL setup and processing data
Sprint 3 | Day 28- 19.01.2025 | Queries on SQL path issues and Flask set up | SQL setup and processing data
Sprint 3 | Day 29- 20.01.2025 | No Impediments | Discussed overall updates
Sprint 3 | Day 30- 21.01.2025 | No Impediments | Discussed overall updates
Sprint 3 | Day 31- 22.01.2025 | Queries on session timeout logic integration | Discussed potential solutions to session timeout issues
Sprint 3 | Day 32- 23.01.2025 | No Impediments | Discussed overall updates
Sprint 3 | Day 33- 24.01.2025 | No Impediments | Discussed overall updates
Sprint 3 | Day 34- 25.01.2025 | Queries on integrating front end with backend | Solved integration issues
Sprint 3 | Day 35- 27.01.2025 | No Impediments | Discussed overall updates
Sprint 3 | Day 36- 28.01.2025 | Queries on integrating front end with backend | Integrated the module components

## Team 2
Sprint | Day | Impediments | Action Taken
Sprint1 | Day 1 - 11/12/24 | Issues with user stories | Discussed and resolved the user story issues.
Sprint1 | Day 2 - 12/12/24 | Task allocation issues and Flask setup doubts | Allocated tasks and resolved Flask setup-related doubts.
Sprint1 | Day 3 - 13/12/24 | No Impediments | Designed and finalized the SQLite database for menu management
Sprint1 | Day 4 - 16/12/24 | No Impediments | Created a GitHub repository for Team 2.
Sprint1 | Day 5 - 17/12/24 | No Impediments | Discussed task completion and workflow with the team.
Sprint 1 | Day 6- 20/12/24 | UI issues and edit functionality not working | Identified, discussed, and resolved UI issues; ensured edit functionality works.
Sprint 1 | Day 7 - 21/12/24 | Issues with export functionality | Diagnosed and fixed the export functionality issues.
Sprint 2 | Day 8 - 27/12/24 | No Impediments | Discussed About Delivery Agent's Dashboard Module and further plannings and task allocations
Sprint 2 | Day 9 - 30/12/24 | No Impediments | Discussed about database finailization for delivery agent module and modification
Sprint 2 | Day 8 - 31/12/24 | Front end and backend issues | Fixed both issues after discussing with team
Sprint 2 | Day 10 - 2/1/25 | No Impediments | Refined Database
Sprint 2 | Day 11 - 4/1/25 | No Impediments | Refined Frontend
Sprint 2 | Day 12 - 5/1/25 | No Impediments | Discussed About Performance page and other related topics
Sprint 2 | Day 13 - 6/1/25 | Delivery status dropdown functionality not working | Disscussed and resolved the issue
Sprint 2 | Day 14 - 7/1/25 | No Impediments | Discussed task completion and workflow with the team.
Sprint2 | Day 15- 8/1/25 | No Impediments | Discussed on retrospection and further planning of pending tasks
Sprint 2 | Day 16 - 9/1/25 | No Impediments | Discussed about Notification task implementation
Sprint 2 | Day 17- 10/1/25 | No Impediments | Discussed about modifications to be done in database
Sprint 2 | Day 18- 13/1/25 | No impediments | Discussed on frontend modification and different approaches for that task to be implemented
Sprint 2 | Day 19- 15/1/25 | No Impediments | Finalized the implementation of the module and updated artifacts
Sprint 2 | Day 20- 16/1/25 | No Impediments | Discussed about the changes to be done in frontend
Sprint 2 | Day 21- 17/1/25 | No Impediments | Finalized the frontend and modified it
Sprint 2 | Day 19- 18/1/25 | No Impediments | Discusses about python tests
Sprint 2 | Day 20- 20/1/25 | No Impediments | Discussed on how integration should be done
Sprint 2 | Day 21-22/1/25 | No Impediments | Assigned team memebers for different parts of Integration
Sprint 2 | Day 22- 23/1/25 | No Impediments | Integrated the module components
Sprint 2 | Day 24- 24/1/25 | No Impediments | Discussed about the frontend changes
Sprint 2 | Day 25- 25/1/25 | No Impediments | Discussed about the issues
Sprint 2 | Day 26- 26/1/25 | Filters category was not working after integration | Discussed and resolved the issue
Sprint 2 | Day 27- 28/1/25 | No Impediments | Discussed on the updates
Sprint 2 | Day 27- 29/1/26 | No Impediments | Worked on Integrated modules

## Team 3
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 - 09/12/2024 | No impediments | Discussed about Product Backlogs
Sprint 1 | Day 2 - 10/12/2024 | No impediments | Finalized the User stories
Sprint 1 | Day 3 - 12/12/2024 | No impediments | Task assignment
Sprint 1 | Day 4- 13/12/2024 | No Impediments | Discussed about design implementation tasks and getting started with assigned tasks
Sprint 1 | Day 5- 15/12/2024 | No Impediments | Discussed the progress of assigned tasks
Sprint 1 | Day 6 - 17-12-2024 | No Impediments | Discussed about progress of assigned tasks
Sprint 1 | Day - 7 - 18-12-2024 | Change in Table structure | Discussed about progress of assigned tasks
Sprint 1 | Day - 7 - 18-12-2024 | No Impediments | Discussed about progress of assigned tasks
Sprint 1 | Day - 8 - 19-12-2024 | No Impediments | Finalizing the overall project works
Sprint 1 | Day - 9 - 20-12-2024 | Queries on Frontend and Backend Functionalities | Discussed the remaining designing, coding part
Sprint 1 | Day - 10 - 21-12-2024 | Integrating Frontend and Backend Functionalities | Finalised our project work
Sprint 2 | Day - 1 - 25-12-2024 | No impediments | Discussed about the User Stories
Sprint 2 | Day - 2 - 27-12-2024 | No impediments | Assigned tasks for Sprint 2
Sprint 2 | Day - 3 - 31-12-2024 | No impediments | Discussed about the Frontend Functionalities
Sprint 2 | Day - 4 - 02-01-2025 | No impediments | Discussed about the Backend Functionalities
Sprint 2 | Day - 5 - 03-01-2025 | No impediments | Discussed the Visualisation and database
Sprint 2 | Day - 6 - 06-01-2025 | No impediments | Discussed about the Pending functionalities
Sprint 2 | Day - 7 - 07-01-2025 | No impediments | Discussed about the Database issues
Sprint 3 | Day - 1 - 09-01-2025 | No impediments | Discussed about the User Stories and Allocated tasks for Sprint 3
Sprint 3 | Day - 2 - 13-01-2025 | Issues in rendering Order section page | Identified and resolved the rendering issue and discussed about progress of assigned tasks
Sprint 3 | Day - 3 - 16-01-2025 | No impediments | Discussed about progress of assigned tasks
Sprint 3 | Day - 4 - 17-01-2025 | No impediments | Discussed about the pending functionalities
Sprint 3 | Day - 5 - 18-01-2025 | Issue in implementing order tracking feature in order summary page | Issue identified, reassigned the task to different person to integrate functionality into the order summary page.
Sprint 3 | Day - 6 - 20-01-2025 | No impediments | Assigned team members to begin testing the user and admin panels
Sprint 3 | Day - 7 - 22-01-2025 | No impediments | Completed the final review of the evaluation.
Sprint 4 | Day - 1 - 24-01-2025 | No impediments | Delegated tasks for testing and integration.
Sprint 4 | Day - 2 - 25-01-2025 | Encountered issues in test cases | Resolved the issue and supported the testing team in progressing with their tasks.
Sprint 4 | Day - 3 - 27-01-2025 | No impediments | Reviewed the testing status and resolved issues with passing test cases.

## Team 4
Sprint | Day | Impediments | Action Taken

## Team 5
Sprint | Day | Impediments | Action Taken